## Sheet1
What | As a | I want to | MoSCoW | Done? | How big | Sprint | Security measures | Legenda
Homepage | user | see a list of news articles | M |  | M | 1 | x | Done
| user | see the date of the news article | S |  | S | 1 | x | W.I.P
| user | see the title of the news article | M |  | S | 1 | x | Not started
| user | see the author of the news article | S |  | S | 1 | x | The time for the task is evaluated in shirt sizes
| user | see the tags of an article | S |  | M | 1 | x | S-M-L-XL
| user | see the picture that goes with the article | S |  | M | 1 | x
| user | have a well sorted list of articles | S |  | S | 2 | x
| Admin | I want to add posts/articles to the website | M |  | L | 3 | No Javascript or SQL injections
| Admin | I want acces to the database with the content | C |  | M | 3 | Only for viewing
Info pages | user | I want to see a small history of the chain | M |  | S | 1 | x
| user | I want to see a foto album of fan art | S |  | M | 1 | x
| user | I want to read about the group | S |  | S | 1 | x
| user | I want to be able to contact them trough a form | S |  | M | 1 | x
| user | I want to read about the characters | C |  | S | 1 | x
| user | I want links to where I can find the podcast and show | S |  | S | 1 | x
search page | user | I want to be able to search the site | M |  | L | 2 | No SQL injections
| user | I want to be able to see the results over more pages | S |  | M | 2 | x
| user | I want to be able to easily see the reults | C |  | M | 2 | x
| user | I want to search from the navigation | S |  | S | 2 | SQL injections
| user | I always want the search conevniently close | C |  | M | 2 | x
| user | I want to see autocomplete for my search tasks | C |  | L | 3 | x
navigation | user | I want to see the logo in the nav bar | C |  | S | 3 | x
| user | I want to see the search option in the nav bar | S |  | S | 2 | x
| user | I want to be able to easily go to the different pages | M |  | S | 1 | x
sidebar | user | I want to find the links to the places where I can find the show | M |  | M | 1 | x
| user | I want to find the links to the places where I can support the show | S |  | M | 1 | x
| user | I want links for the statistics pages | C |  | M | 1 | x
login | Admin | login to the website | M |  | XL | 3 | No SQL or Javascript injections
Statistics | Admin | I want to be able to see a google analytics page for the website. | C |  | M | 3 | x